## Slide 1: Bachelor project kickoff meeting
Project 4.6: “Optimizing the performance of neural networks using evolutionary computing”

## Slide 2: Goals for this kickoff meeting
Get to know each other
Share practical information about the project
Answer questions from your side

## Slide 3: Roles
Counsellor: Negin Harandi (Negin.Harandi@ghent.ac.kr)
  Week by week guidance (research goals, technical aid, general advice)
  The expert on the topic
Supervisor: Joris Vankerschaver (Joris.Vankerschaver@ghent.ac.kr)
  Guidance, but not week by week  (unless I can find the time)
Advisory: Utku Özbulak (utku.ozbulak@ghent.ac.kr)

## Slide 4: Practical things for you to do
Before Status Meeting 1:
Establish shared communication channel (e.g. KakaoTalk)
Set up way to store shared information. Suggestions:
  Google Drive for papers, graphs, images, …
  GitHub for code (we can help with this)
Establish shared log book, to keep track of
  Hours spent on computational phase
  Hypotheses tested, conclusions, …
Set up Python environment for ML (we can help with this)

## Slide 5: Deadlines and status meetings
Phase 1: Literature study (weeks 0-5)
  Acquire background in the chosen topic
  Status meeting 1 (week 2/3): review of reading done so far, bibliography of reading, …
  Draft introduction chapter: due week 5
Phase 2: Experimental phase (weeks 2-9)
  Put your ideas and hypotheses to the test
  Status meeting 2 (week 6/7): what have you learned so far from computational experiments?
  30 hours of work (excluding meetings, planning) per student over the whole phase

## Slide 6: Tips and tricks
Start with the simple things
Leave enough time for the simple things
Think in terms of research questions
  What is the relevance? What will your work establish?
Keep track of how you spend your time, dead ends, etc.
  Failures are often the harbringers of success
Combine your biology/biotech knowledge with bio data science.
  Pure data science is dead, pure biology is dumb. Combining the two is where new insights can be found.
  You know more biology than us!
  You will be quizzed on this during the final presentation.

## Slide 7: What’s on your mind?